## Pre-filled Starter Sheet
Purpose Conveys the scope of various tasks that need to be coordinated to build and launch the product/feature | What is the task? Based on the purpose, select the appropriate from the drop-down | Who is the task owner? Does the following to finish task: 1. Schedule and run meetings 2. Gather feedback and share updates 3. Follow-up with stakeholders | Whose involvement is needed to accomplish the task ? Please select one from the drop-down list of your identified stakeholders | What is their role? Select the stakeholder's role from the drop-down. Note: 'Scrum Team' role is applicable to stakeholder 'Scrum Team' only | By when, does the task need to be completed? Select milestone keeping in mind nature of the task,downstream effects of delaying task
Evangelize internally | Setup PRD review meeting to receive feedback | Product Manager | Head of Product |  | Set a target week
Contributors (Consulted for their opinions or expertise to help with project decisions)
| Setup meeting to kickoff project with the scrum team |  | Scrum Team | Scrum Team (Involved directly in product development efforts)
Involve legal and compliance |  | Product Manager |  |  | Set a target week
Incorporate stakeholders feedback |  | Product Manager | Product Designer | Scrum Team (Involved directly in product development efforts)
Initiate and maintain feedback loop |  | Product Manager
Plan development work | Setup solution feasibility discussions to understand the work involved/identify inter-dependencies and potential risks | Product Manager | Scrum Team | Scrum Team (Involved directly in product development efforts)
Engineering Lead
Manage product/feature testing | Share and review the project's test strategy |  | Scrum Team | Scrum Team (Involved directly in product development efforts)
Setup analytics tracking | Create a project-specific communication channel (in Slack etc) to share insights from customer meetings/usability tests/data analysis |  | Scrum Team | Scrum Team (Involved directly in product development efforts)
Prepare for every sprint |  |  | Scrum Team | Scrum Team (Involved directly in product development efforts)
Create tickets for each sprint based on the analytics tracking requirements
Product Manager
Coordinate product/feature launch |  |  | Product Manager
Product Manager
Communicate project progress |  | Product Manager
Receive product/feature sign-off | Setup meeting to demo the feature and conduct end-to-end feature testing to identify bugs and receive feedback | Product Manager
Impacted Product Managers
Note on A20: these should be 11a, 11b, 11c -Unknown Hi +michele.cavaioni@udacity.com It is usually in the same meeting or two different meetings, but I have kept as one over here. updated the numbering -Yuva Sharanyah Murugan

## Help Information
Stakeholders identified for the project
Head of Product
Impacted Product Managers (Your product/feature impact the product/feature they mange directly or indirectly)
Cross-functional Stakeholders (Representation from these areas: Customer Service, Marketing (includes Product Marketing) and Operations )
Scrum Team (Mentioned here)
Legal and Compliance
Customer Service